## Seungwon
To-do list
To be completed by: |  | 2022-12-10 |  | Final Project
Deadline: |  | 2022-12-13 |  | Date: 11/29/2022
Final Project
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2022-11-27 | 2022-11-27 | 2022-11-27 | 1 day | decide the time-table for meetups via discord
100% | Preparation | 2022-11-28 | 2022-11-28 | 2022-11-28 | 1 day | Make sure all the team members has read the project specification
100% | Meeting plan | 2022-11-29 | 2022-11-29 | 2022-11-29 | 1 day | First meeting on discord, divided all the tasks equally among the group members.
100% | Creating Domains, Constraints, default values | 2022-11-29 | 2022-12-01 | 2022-12-01 | 3 days | Creating UDT and top level domains, Constraints, default values and validation rules with 2 or 3 erwin reports.
75% | Creating CDM and LDM with subject areas | 2022-12-01 | 2022-12-03 | 2022-12-03 | 3 days | Convert the RawEuropeanCarManufacturer to CDM and LDM with the use of subject areas also adding 2 or 3 erwin reports.
100% | Creating PDM, adding table DBSecurity.UserAuthorization | 2022-12-03 | 2022-12-05 | 2022-12-05 | 3 days | Convert the RawEuropeanCarManufacture into PDM adding 2 or 3 reports, Create a new fully qualified table called DBSecurity.UserAuthorization, alter all the tables by adding extra columns.
100% | Creating triggers, and porting data | 2022-12-05 | 2022-12-07 | 2022-12-07 | 3 days | Creating triggers and loading data to Postgres and mysql.
100% | Create a MongoDB, port data from SQL to MongoDB | 2022-12-07 | 2022-12-09 | 2022-12-09 | 3 days | Export the Script and Data from ssms, Create a backup of our final database solution( ClassTimeLastNameFirstNameBIClass.bak)
60% | Paperwork | 2022-12-09 | 2022-12-10 | 2022-12-10 | 2 days | Start working on ppt, explaining each team members work and recording them, documentation, vhdx file.
75% | Final Checkup | 2022-12-11 | 2022-12-12 | 2022-12-12 | 2 days | Follow up with the team member last time to check for any bugs in the code. Make sure the project contains the views of all team members,from individual team members.
100% | Handoff | 2022-12-13 | 2022-12-13 | 2022-12-13 | 1 day | Handoff- the project atleast 2-3 hours before the due date.

## David
To-do list
To be completed by: |  | 2022-12-10 |  | Final Project
Deadline: |  | 2022-12-13 |  | Date: 11/29/2022
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2022-11-27 | 2022-11-27 | 2022-11-27 | 1 day | decide the time-table for meetups via discord
100% | Preparation | 2022-11-28 | 2022-11-28 | 2022-11-28 | 1 day | Make sure all the team members has read the project specification
100% | Meeting plan | 2022-11-29 | 2022-11-29 | 2022-11-29 | 1 day | First meeting on discord, divided all the tasks equally among the group members.
100% | Creating Domains, Constraints, default values | 2022-11-29 | 2022-12-01 | 2022-12-01 | 3 days | Creating UDT and top level domains, Constraints, default values and validation rules with 2 or 3 erwin reports.
75% | Creating CDM and LDM with subject areas | 2022-12-01 | 2022-12-03 | 2022-12-03 | 3 days | Convert the RawEuropeanCarManufacturer to CDM and LDM with the use of subject areas also adding 2 or 3 erwin reports.
100% | Creating PDM, adding table DBSecurity.UserAuthorization | 2022-12-03 | 2022-12-05 | 2022-12-05 | 3 days | Convert the RawEuropeanCarManufacture into PDM adding 2 or 3 reports, Create a new fully qualified table called DBSecurity.UserAuthorization, alter all the tables by adding extra columns.
100% | Creating triggers, and porting data | 2022-12-05 | 2022-12-07 | 2022-12-07 | 3 days | Creating triggers and loading data to Postgres and mysql.
100% | Create a MongoDB, port data from SQL to MongoDB | 2022-12-07 | 2022-12-09 | 2022-12-09 | 3 days | Export the Script and Data from ssms, Create a backup of our final database solution( ClassTimeLastNameFirstNameBIClass.bak)
60% | Paperwork | 2022-12-09 | 2022-12-10 | 2022-12-10 | 2 days | Start working on ppt, explaining each team members work and recording them, documentation, vhdx file.
75% | Final Checkup | 2022-12-11 | 2022-12-12 | 2022-12-12 | 2 days | Follow up with the team member last time to check for any bugs in the code. Make sure the project contains the views of all team members,from individual team members.
100% | Handoff | 2022-12-13 | 2022-12-13 | 2022-12-13 | 1 day | Handoff- the project atleast 2-3 hours before the due date.

## Cristian
To-do list
To be completed by: |  | 2022-12-10 |  | Final Project
Deadline: |  | 2022-12-13 |  | Date: 11/29/2022
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2022-11-27 | 2022-11-27 | 2022-11-27 | 1 day | decide the time-table for meetups via discord
100% | Preparation | 2022-11-28 | 2022-11-28 | 2022-11-28 | 1 day | Make sure all the team members has read the project specification
100% | Meeting plan | 2022-11-29 | 2022-11-29 | 2022-11-29 | 1 day | First meeting on discord, divided all the tasks equally among the group members.
100% | Creating Domains, Constraints, default values | 2022-11-29 | 2022-12-01 | 2022-12-01 | 3 days | Creating UDT and top level domains, Constraints, default values and validation rules with 2 or 3 erwin reports.
75% | Creating CDM and LDM with subject areas | 2022-12-01 | 2022-12-03 | 2022-12-03 | 3 days | Convert the RawEuropeanCarManufacturer to CDM and LDM with the use of subject areas also adding 2 or 3 erwin reports.
100% | Creating PDM, adding table DBSecurity.UserAuthorization | 2022-12-03 | 2022-12-05 | 2022-12-05 | 3 days | Convert the RawEuropeanCarManufacture into PDM adding 2 or 3 reports, Create a new fully qualified table called DBSecurity.UserAuthorization, alter all the tables by adding extra columns.
100% | Creating triggers, and porting data | 2022-12-05 | 2022-12-07 | 2022-12-07 | 3 days | Creating triggers and loading data to Postgres and mysql.
100% | Create a MongoDB, port data from SQL to MongoDB | 2022-12-07 | 2022-12-09 | 2022-12-09 | 3 days | Export the Script and Data from ssms, Create a backup of our final database solution( ClassTimeLastNameFirstNameBIClass.bak)
60% | Paperwork | 2022-12-09 | 2022-12-10 | 2022-12-10 | 2 days | Start working on ppt, explaining each team members work and recording them, documentation, vhdx file.
75% | Final Checkup | 2022-12-11 | 2022-12-12 | 2022-12-12 | 2 days | Follow up with the team member last time to check for any bugs in the code. Make sure the project contains the views of all team members,from individual team members.
100% | Handoff | 2022-12-13 | 2022-12-13 | 2022-12-13 | 1 day | Handoff- the project atleast 2-3 hours before the due date.

## Rishi
To-do list
To be completed by: |  | 2022-12-10 |  | Final Project
Deadline: |  | 2022-12-13 |  | Date: 11/29/2022
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2022-11-27 | 2022-11-27 | 2022-11-27 | 1 day | decide the time-table for meetups via discord
100% | Preparation | 2022-11-28 | 2022-11-28 | 2022-11-28 | 1 day | Make sure all the team members has read the project specification
100% | Meeting plan | 2022-11-29 | 2022-11-29 | 2022-11-29 | 1 day | First meeting on discord, divided all the tasks equally among the group members.
100% | Creating Domains, Constraints, default values | 2022-11-29 | 2022-12-01 | 2022-12-01 | 3 days | Creating UDT and top level domains, Constraints, default values and validation rules with 2 or 3 erwin reports.
75% | Creating CDM and LDM with subject areas | 2022-12-01 | 2022-12-03 | 2022-12-03 | 3 days | Convert the RawEuropeanCarManufacturer to CDM and LDM with the use of subject areas also adding 2 or 3 erwin reports.
100% | Creating PDM, adding table DBSecurity.UserAuthorization | 2022-12-03 | 2022-12-05 | 2022-12-05 | 3 days | Convert the RawEuropeanCarManufacture into PDM adding 2 or 3 reports, Create a new fully qualified table called DBSecurity.UserAuthorization, alter all the tables by adding extra columns.
100% | Creating triggers, and porting data | 2022-12-05 | 2022-12-07 | 2022-12-07 | 3 days | Creating triggers and loading data to Postgres and mysql.
100% | Create a MongoDB, port data from SQL to MongoDB | 2022-12-07 | 2022-12-09 | 2022-12-09 | 3 days | Export the Script and Data from ssms, Create a backup of our final database solution( ClassTimeLastNameFirstNameBIClass.bak)
60% | Paperwork | 2022-12-09 | 2022-12-10 | 2022-12-10 | 2 days | Start working on ppt, explaining each team members work and recording them, documentation, vhdx file.
75% | Final Checkup | 2022-12-11 | 2022-12-12 | 2022-12-12 | 2 days | Follow up with the team member last time to check for any bugs in the code. Make sure the project contains the views of all team members,from individual team members.
100% | Handoff | 2022-12-13 | 2022-12-13 | 2022-12-13 | 1 day | Handoff- the project atleast 2-3 hours before the due date.

## Amarjit
To-do list
To be completed by: |  | 2022-12-10 |  | Final Project
Deadline: |  | 2022-12-13 |  | Date: 11/29/2022
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2022-11-27 | 2022-11-27 | 2022-11-27 | 1 day | decide the time-table for meetups via discord
100% | Preparation | 2022-11-28 | 2022-11-28 | 2022-11-28 | 1 day | Make sure all the team members has read the project specification
100% | Meeting plan | 2022-11-29 | 2022-11-29 | 2022-11-29 | 1 day | First meeting on discord, divided all the tasks equally among the group members.
100% | Creating Domains, Constraints, default values | 2022-11-29 | 2022-12-01 | 2022-12-01 | 3 days | Creating UDT and top level domains, Constraints, default values and validation rules with 2 or 3 erwin reports.
75% | Creating CDM and LDM with subject areas | 2022-12-01 | 2022-12-03 | 2022-12-03 | 3 days | Convert the RawEuropeanCarManufacturer to CDM and LDM with the use of subject areas also adding 2 or 3 erwin reports.
100% | Creating PDM, adding table DBSecurity.UserAuthorization | 2022-12-03 | 2022-12-05 | 2022-12-05 | 3 days | Convert the RawEuropeanCarManufacture into PDM adding 2 or 3 reports, Create a new fully qualified table called DBSecurity.UserAuthorization, alter all the tables by adding extra columns.
100% | Creating triggers, and porting data | 2022-12-05 | 2022-12-07 | 2022-12-07 | 3 days | Creating triggers and loading data to Postgres and mysql.
100% | Create a MongoDB, port data from SQL to MongoDB | 2022-12-07 | 2022-12-09 | 2022-12-09 | 3 days | Export the Script and Data from ssms, Create a backup of our final database solution( ClassTimeLastNameFirstNameBIClass.bak)
60% | Paperwork | 2022-12-09 | 2022-12-10 | 2022-12-10 | 2 days | Start working on ppt, explaining each team members work and recording them, documentation, vhdx file.
75% | Final Checkup | 2022-12-11 | 2022-12-12 | 2022-12-12 | 2 days | Follow up with the team member last time to check for any bugs in the code. Make sure the project contains the views of all team members,from individual team members.
100% | Handoff | 2022-12-13 | 2022-12-13 | 2022-12-13 | 1 day | Handoff- the project atleast 2-3 hours before the due date.

## Rabina
To-do list
To be completed by: |  | 2022-12-10 |  | Final Project
Deadline: |  | 2022-12-13 |  | Date: 11/29/2022
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2022-11-27 | 2022-11-27 | 2022-11-27 | 1 day | decide the time-table for meetups via discord
100% | Preparation | 2022-11-28 | 2022-11-28 | 2022-11-28 | 1 day | Make sure all the team members has read the project specification
100% | Meeting plan | 2022-11-29 | 2022-11-29 | 2022-11-29 | 1 day | First meeting on discord, divided all the tasks equally among the group members.
100% | Creating Domains, Constraints, default values | 2022-11-29 | 2022-12-01 | 2022-12-01 | 3 days | Creating UDT and top level domains, Constraints, default values and validation rules with 2 or 3 erwin reports.
75% | Creating CDM and LDM with subject areas | 2022-12-01 | 2022-12-03 | 2022-12-03 | 3 days | Convert the RawEuropeanCarManufacturer to CDM and LDM with the use of subject areas also adding 2 or 3 erwin reports.
100% | Creating PDM, adding table DBSecurity.UserAuthorization | 2022-12-03 | 2022-12-05 | 2022-12-05 | 3 days | Convert the RawEuropeanCarManufacture into PDM adding 2 or 3 reports, Create a new fully qualified table called DBSecurity.UserAuthorization, alter all the tables by adding extra columns.
100% | Creating triggers, and porting data | 2022-12-05 | 2022-12-07 | 2022-12-07 | 3 days | Creating triggers and loading data to Postgres and mysql.
100% | Create a MongoDB, port data from SQL to MongoDB | 2022-12-07 | 2022-12-09 | 2022-12-09 | 3 days | Export the Script and Data from ssms, Create a backup of our final database solution( ClassTimeLastNameFirstNameBIClass.bak)
60% | Paperwork | 2022-12-09 | 2022-12-10 | 2022-12-10 | 2 days | Start working on ppt, explaining each team members work and recording them, documentation, vhdx file.
75% | Final Checkup | 2022-12-11 | 2022-12-12 | 2022-12-12 | 2 days | Follow up with the team member last time to check for any bugs in the code. Make sure the project contains the views of all team members,from individual team members.
100% | Handoff | 2022-12-13 | 2022-12-13 | 2022-12-13 | 1 day | Handoff- the project atleast 2-3 hours before the due date.